## Sheet1
Stage | Expected Start Date | Expected Completion Date | Products/Deliverables/Outcomes
1.Project Initiation | 2018-12-10 | 2018-12-14 | Project Initiation Document Submission
2.Investigation and research | 2019-01-25 | 2019-02-01 | Learning Week
| 2019-01-25 | 2019-05-02 | Draft Report
3. Stage 1 | 2019-02-04 | 2019-02-08 | Stage 1 Completion ¦ Design Architecture, UI and Database.
| 2019-02-07 | 2019-02-07 | Highlight Report 1
4. Stage 2 | 2019-02-11 | 2019-02-15 | Stage 2 Completion ¦ Implement User account registration and authentication.
| 2019-02-14 | 2019-02-14 | Highlight Report 2
|  | 2019-02-14 | Data Review
5. Stage 3 | 2019-02-18 | 2019-02-22 | Stage 3 Completion ¦ Implment the Google Cloud Vision API to identify the users uploaded photo.
| 2019-02-21 | 2019-02-21 | Highlight Report 3
6. Stage 4 | 2019-02-25 | 2019-03-01 | Stage 4 Completion ¦ Implement the Wikipedia API to provide information on the identified plant
| 2019-02-28 | 2019-02-28 | Highlight Report 4
7. Stage 5 | 2019-03-04 | 2019-03-08 | Stage 5 Completion ¦ Implement Google maps within the APP and populate pins with users images.
| 2019-03-07 | 2019-03-07 | Highlight Report 5
8. Stage 6 | 2019-03-11 | 2019-03-15 | Stage 6 Completion¦ Implement ability for user to view information on each selected pin and view other user profiles.
| 2019-03-14 | 2019-03-14 | Highlight Report 6
9. Stage 7 | 2019-03-19 | 2019-03-22 | Stage 7 Completion ¦ User Testing, implementing fixes for bugs. Add user profiles for other users to view
| 2019-03-21 | 2019-03-21 | Highlight Report 7
10. Stage 8 | 2019-03-25 | 2019-03-29 | Stage 8 Completion ¦ Fix bugs and complete backlog.
|  | 2019-03-26 | Code Review
| 2019-03-28 | 2019-03-28 | Highlight Report 8
| 2019-04-02 | 2019-04-04 | Poster
Easter holiday | 2019-04-08 | 2019-04-26 | Easter Break (3 Week Buffer)
|  | 2019-05-16 | Final Deliverable
Notes: The Highlight Reports are due on thursdays, I will be aiming to complete stages on Friday