## Sheet1
| User Story | Start Date | End Date
Sprint 1 |  | 2019-02-04 | 2019-02-08 | Design Architecture, UI, Database, User stories
Sprint 2 |  | 2019-02-11 | 2019-02-15 | Initial app development, Implement User & Admin account registration and authentication.
1
2
3
4
5
6
7
20
Sprint 3 |  | 2019-02-18 | 2019-02-22 | Implement the Google cloud vision API to identify the users uploaded photo
8
9
10
24
25
Sprint 4 |  | 2019-02-25 | 2019-03-01 | Implement the Wikipedia API to provide information on the identified plant, enable the user to identify their own plant
11
12
13
Sprint 5 |  | 2019-03-04 | 2019-03-08 | Implement Google maps within the app and populate pins with users images.
14
15
Sprint 6 |  | 2019-03-11 | 2019-03-15 | Implement ability for users to view information on each selected pin and view other user profiles
16
17
18
19
20
21
22
23
Sprint 7 |  | 2019-03-18 | 2019-03-22 | User Testing, implementing fixes for bugs, add user profiles for other users to view
Sprint 8 |  | 2019-03-25 | 2019-03-29 | Fix bugs and complete backlog